## Project Motivation
Table 2: Example Project Motivation Table
Zone | Proj. No. | Potential Project Name | Cost Estimate ($M) | New Develop-ment | Hydraulics Correction | High Risk Ranking | I&I Reduction | >80% of Useful Life | >100% of Useful Life | Leak & Break History | Qualifies Funding | Road Project | Other | No. of Motivations
1 | 1a | North Shore Dr Sewer Lining | 1 |  |  |  | X |  |  |  | X |  |  | 2
| 1b | Peterson Ave Road Widening | 2.4 | [8 empty] | X |  | 1
| 1c | Grande Isles New Sewer System | 1.5 | X | [7 empty] | X | City Council Agenda Item | 3
2 | 2a | Highway 66 Redundant Interceptor | 6.2 |  | X | [8 empty] | 1
| 2b | High View Development New Sewers & Lift Station | 4.1 | X | [7 empty] | X |  | 2
3 | 3a | Lift Station No. 21 Rehabilitation | 0.5 |  |  |  |  | X | [5 empty] | 1
| 3b | Jupiter Dr. Force Main Replacement | 5.2 |  |  | X |  | X |  | X |  |  |  | 3
4 | 4a | Regional Pump Station Expansion | 8 | X | [9 empty] | 1
| 4b | Lift Station No. 12 Rehabilitation | 0.6 |  |  | X |  | X | X |  |  |  |  | 3
| 4c | Cottage River HDD Crossing | 3.6 |  | X | [7 empty] | Riverbank Restoration | 2
| 4d | N. 68th St Sewer Lining | 1.5 |  |  |  | X | X | X |  | X |  |  | 4
Multi | M1 | Aged Manhole Lining | 0.8 |  |  |  | X | X |  |  | X |  |  | 3
| M2 | Aerial Crossing Repairs | 4.1 |  |  | X |  | X | [5 empty] | 2
| M3 | Air Relief Valve Replacements | 0.6 |  |  |  |  | X |  | X |  |  |  | 2
Total |  |  | 40.1 | 13.6 | 9.8 | 9.9 | 3.3 | 13.3 | 2.1 | 5.8 | 3.3 | 8 | 5.1 | -

## CIP Budget Schedule
Table 3: Example CIP Budget Schedule (Phase coloring: study, design, bid, construction) (All costs in $M)
Zone | Proj. No. | Potential Project Name | Cost Estimate ($M) | 2023 | [7 empty] | 2025
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | check math, $0 = ok
1 | 1a | North Shore Dr Sewer Lining | 1 | - | - | 0.05 | 0.05 | 0 | 0 | 0.2 | 0.2 | 0.3 | 0.2 | - | - | 0
| 1b | Peterson Ave Road Widening | 2.4 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.3 | 0.4 | 0.6 | 0.6 | 0.2 | - | - | 0
| 1c | Grande Isles New Sewer System | 1.5 | 0.05 | 0.05 | 0.1 | 0 | 0 | 0.2 | 0.2 | 0.4 | 0.4 | 0.1 | - | - | 0
2 | 2a | Highway 66 Redundant Interceptor | 6.2 | - | - | 0.2 | 0.3 | 0.2 | 0 | 0 | 0.8 | 1.2 | 1.4 | 1.6 | 0.5 | 0
| 2b | High View Development New Sewers & Lift Station | 4.1 | - | - | 0.1 | 0.2 | 0.2 | 0 | 0 | 0.6 | 0.8 | 1 | 1 | 0.2 | 0
3 | 3a | Lift Station No. 21 Rehabilitation | 0.5 | - | - | - | 0.03 | 0.02 | 0 | 0 | 0.05 | 0.1 | 0.2 | 0.1 | - | 0
| 3b | Jupiter Dr. Force Main Replacement | 5.2 | - | 0.1 | 0.2 | 0.2 | 0 | 0 | 0.6 | 1 | 1.3 | 1.4 | 0.4 | - | 0
4 | 4a | Regional Pump Station Expansion | 8 | 0.1 | 0.1 | 0.2 | 0.4 | 0.3 | 0 | 0 | 1.2 | 1.6 | 2 | 1.8 | 0.3 | 0
| 4b | Lift Station No. 12 Rehabilitation | 0.6 | - | - | - | 0.03 | 0.02 | 0 | 0 | 0.05 | 0.2 | 0.2 | 0.1 | - | 0
| 4c | Cottage River HDD Crossing | 3.6 | - | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.5 | 0.7 | 0.9 | 0.9 | 0.2 | 0
| 4d | N. 68th St Sewer Lining | 1.5 | 0.05 | 0.05 | 0.1 | 0 | 0 | 0.2 | 0.2 | 0.4 | 0.4 | 0.1 | - | - | 0
Multi | M1 | Aged Manhole Lining | 0.8 | 0.05 | 0.05 | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.1 | - | - | - | - | 0
| M2 | Aerial Crossing Repairs | 4.1 | 0.1 | 0.2 | 0.2 | 0 | 0 | 0.6 | 0.8 | 1 | 1 | 0.2 | - | - | 0
| M3 | Air Relief Valve Replacements | 0.6 | - | - | 0.02 | 0.02 | 0 | 0 | 0.06 | 0.2 | 0.2 | 0.1 | - | - | 0
Quarter Total |  |  | 40.1 | 0.45 | 0.75 | 1.37 | 1.33 | 0.94 | 1.5 | 2.76 | 7.1 | 8.8 | 8 | 5.9 | 1.2 | 0
Annual Total |  |  |  | 2023 Q1: 3.9; 2023 Q1: 12.3; 2025 Q1: 23.9 | 0