## To-do list
TO DO LIST | [5 empty] | TODAY'S PROGRESS | This Week | 3 | Today Completed | 1
CATEGORY | DESCRIPTION | DUE | PRIORITY | STATUS | NOTES | 50% | Tomorrow | 1
Sub | Review proposal for surveying | 2025-06-28 | Medium | Completed | Move this to completed tab |  | Today | 2
Sub | Review change proposal from geotech | 2025-06-30 | High | In progress |  | YELLOW = DO NEXT
Design Issue | Raise Elevation of Bldg 302 | 2025-06-28 | High | In progress | Meet w/ Sarah
Client | Respond to question on ADA compliance. Check with architect. | 2025-07-01 | Medium | In progress
Invoicing | Review draft Invoice #2 | 2025-06-30 | Medium | Pending
Changes | Prepare change proposal for adding utility locates to scope | 2025-07-03 | High | In progress | Incorporate civil comments
Civil | Schedule meeting to review base map with civil team | 2025-07-05 | Medium | Pending
Structural | Schedule meeting to review building layout and room sizes | 2025-07-05 | Low | Pending
Electrical | Assign internal reviewer for subconsultant electrical work | 2025-06-29 | Medium | Pending
Quality | Schedule meeting for quality review assignments | 2025-07-05 | High | Pending
Cost Estimate | Send estimator draft building layout for high level costing | 2025-07-13 | Low | Pending

## Completed
COMPLETION LIST |  |  |  | This Week | 3 | Today Completed | #REF!
CATEGORY | DESCRIPTION | DATE DONE | NOTES | Tomorrow | 0
Sub | Issue PO for electrical sub | 2025-02-05 |  | Today | 3
Meetings | Distribute KO meeting notes | 2025-02-08
Resources | Check with resource manager for vacation coverage for Ben | 2025-02-10