## Example Log
Permit Name | Agency | Submittal Date |  | Resubmittal Date |  | Approval Date |  | Status and Notes
|  | Projected | Actual | Projected | Actual | Projected | Actual
Zoning Permit | City Dept of Community Development | - | 2025-03-11 | - | 2025-04-18 | - | 2025-06-14 | Height restriction variance
Site Plan Approval | City Dept of Community Development | - | 2025-04-18 | - | 2025-05-21 | - | 2025-06-14 | Sidewalk added
County Planning Approval | County Planning Dept | - | 2025-04-03 | - | 2025-04-18 | - | 2025-06-06 | Sidewalk added, road widening, survey submitted
Road Opening Permit | County Dept of Highways | - | 2025-04-18 | - | N/A | - | 2025-05-22 | Driveway and sidewalk improvements
Soil Erosion Control Approval | City Dept of Community Development | - | 2025-04-18 | - | N/A | - | 2025-06-01
Tree Removal Permit | City Dept of Community Development | - | 2025-03-11 | - | 2025-05-21 | 2025-06-21 | - | Comments received on 5/02/2025
Industrial Pretreatment Modification | County Utility Authority | - | 2025-02-05 | - | 2025-04-04 | - | 2025-05-14 | Sent request letter with description of system and changes
Building Permit "Dry Run" | City Building Dept | - | 2025-02-12 | - | N/A | - | 2025-03-11 | Preliminary review of draft plans, comments received and addressed
Building Permit & Trade Permits | City Building Dept | - | 2025-03-18 | - | 2025-05-29 | 2025-07-02 | - | Includes trade permits: Mechanical, Electrical, Plumbing, Fire Protection